## Tahapan
Rencana implementasi Cineva Content Studio
22 Oktober 2026. Rencana, belum implementasi. Package existing belum full parity.
Tahap | Hasil | Dependency | Fondasi HOTS / tambahan | Lingkup implementasi | Acceptance gate
P0 | Kontrak, schema, scope dan baseline | Tidak ada | tenant-*; domain-kit; transaction-kit | Package delta, OpenAPI, scope company/personal, physical schema authoritative | Cross-context API/media/worker/SSE ditolak; EAV terjaga; migration plan sebelum SQL
P1 | Editor, template, brand kit, render | P0 kontrak | ui-kit; dynamic-form; content core baru | Visual editor, 6–10 desain awal, galeri 64+ kapasitas, 4:5/9:16, logo/watermark/closing | Output pixel benar, teks tidak terpotong, preview/export sama, save/version/reload
P2 | AI dari link, teks dan ide | P1 model konten | domain-kit proposal; AI/extractor adapter baru | Source extraction, provenance, schema-validated draft, model nyata, fallback link unsupported | Malformed/timeout/cancel/quota aman; AI tidak publish otomatis; retry tidak double-charge
P3 | QC, kalender, durable scheduler | P0 server + P1 revision | Workflow existing; transaction-kit; app-core/notification-kit | Week/month/list; immutable approved version; per-target status; lease/recovery/reconcile | Restart/2 workers/cancel race/rollback/timezone; unknown tidak blind retry
P4 | Empat konektor sosial live | P3 + developer apps/akun test | Social-publishing module; engine-client extension | Instagram kandidat pertama, lalu Facebook/Threads/TikTok; capabilities per akun/format | Consent → post ID → inspeksi live tiap provider; revoke/token expiry/rate-limit diuji
P5 | Analytics dan AI insight | P4 post IDs + metric permission | Social-insights module; ui-kit/chart; table-engine | Period/account/platform filters, raw snapshots, top post/template, evidence-linked insight | Angka reconcile, unsupported null, snapshot tidak double-count, sample/periode jelas
P6 | Kuota, team dan release | P1–P5 full parity | Entitlement adapter; tenant-*; transaction-kit | Server quota ledger, audit, worker deployment, canary, rollback, package bundle | End-to-end nyata dan regression campaign/marketplace/payout/booking; no Kantor dependency

## Cakupan
Cakupan fitur referensi client
14 requirement utama. Tutorial/afiliasi/API-MCP perlu requirement detail tersendiri.
ID | Gambar | Requirement | Tahap | Package / pemilik | Gap existing | Bukti wajib sebelum selesai
R01 | 1 | AI carousel dari link/teks/ide | P2 | domain-kit + content-studio/AI adapter | Belum ada inference konten | Live model + draft validation + fallback tiap source
R02 | 1 | Slide count, bahasa, rasio | P1/P2 | Content core/renderer + form/ui-kit | Renderer konten baru diperlukan | Dimensi/order benar; bahasa/length constraints
R03 | 2,7 | Template gallery/filter/default | P1 | ui-kit + katalog content-studio | Slider UI bukan desain template | 64 fixture filterable; jumlah desain actual eksplisit
R04 | 3,6 | Kalender week/month/list | P3 | ui-kit composition + publishing module | DayPicker/scheduling-kit bukan scheduler | Per-target status, timezone, reschedule/cancel
R05 | 4 | Output sosial nyata | P1/P4 | Renderer + provider connector | Tidak dibuktikan oleh screenshot client | File render dan post pada akun test nyata
R06 | 5 | Multi-platform/multi-account | P4 | tenant-* + social provider registry | OAuth/provider adapters baru | Empat provider lulus gate masing-masing
R07 | 3,5,6 | Publish now/scheduled/status gagal | P3/P4 | transaction-kit + durable worker extension | Outbox bukan delayed queue lengkap | Restart/race/reconcile/partial-success
R08 | 5 | Feed/story/caption/hashtag/audio | P1/P4 | Form options + capability adapter | Bergantung format/akun/API provider | Unsupported eksplisit; audio sesuai API, tanpa janji FYP
R09 | 8 | Brand kit logo/watermark/penutup | P1 | content core + ui-kit + entitlement | Theme aplikasi bukan brand kit output | Preview/export sama; policy brand/provider
R10 | 9 | Views/interactions/ER/followers | P5 | Insights collector + metric contract | Existing snapshot manual dummy | Raw→dashboard reconcile; unsupported null
R11 | 9,10 | Tren/top post/template ranking | P5 | Projection + table-engine/ui-kit chart | Agregasi dan attribution baru | Periode/sample/denominator benar
R12 | 10 | AI insight jam/hari/template | P5 | Evidence insight adapter | Assistant job bukan analisis sosial | Sumber/periode/sample dapat ditelusuri
R13 | 1,8 | Paket/kuota/team | P0/P6 | tenant-* + entitlement/usage ledger | Starter/Pro existing simulasi job | Server enforcement dan quota concurrency
R14 | 3,5 | Draft/revisi/QC/history | P3 | Workflow existing + domain revision adapter | Dummy guards perlu backend persistence | Approved revision locked dan regresi

## Package
Package HOTS dan keputusan pemakaian
Metadata dan hash src aktual dibaca 22 Oktober. Source parity bukan bukti runtime.
Package | Cineva | HOTS reference | Source parity | Delta files | Keputusan | Lokasi sumber
@hots/dynamic-form | 0.1.0-cineva.2 | 0.1.1 | Berbeda | 3 | Reuse forms; reconcile upstream whitelist and local unique IDs. | 1.Frontend/dynamic-form
@hots/service-form-runtime | 0.1.0 | 0.1.0 | Sama | 0 | Reuse normalization; verify actual submit integration. | 1.Frontend/service-form-runtime
@hots/ui-kit | 0.2.0-cineva.1 | 0.2.0 | Sama | 0 | Reuse controls/chart; slider and date picker are not content/scheduler engines. | 1.Frontend/packages/ui-kit
@hots/app-core | 0.6.0-cineva.1 | 0.6.0 | Berbeda | 1 | Reuse HTTP/SSE/media URLs; server owns social tokens. | 1.Frontend/packages/app-core
@hots/table-engine | 0.2.0-cineva.2 | 0.3.0 | Berbeda | 12 | Review upstream 0.3.0 actions versus local split/refactor; no wholesale overwrite. | 1.Frontend/packages/table-engine
@hots/engine-client | 0.2.0-cineva.1 | 0.2.1 | Berbeda | 3 | Add optional content/social clients; preserve legacy envelopes. | 1.Frontend/packages/engine-client
@hots/domain-kit | 0.1.0-cineva.2 | 0.1.0 | Sama | 0 | Reuse sync command/proposal/schema guards; inference is new server adapter. | 1.Frontend/packages/domain-kit
@hots/scheduling-kit | 0.1.0-cineva.2 | 0.1.0 | Sama | 0 | Keep pure resource availability; separate publishing scheduler. | 1.Frontend/packages/scheduling-kit
@hots/page-engine | 0.1.0 | 0.1.0 | Sama | 0 | Layout/CSS only; content renderer still needed. | 1.Frontend/packages/page-engine
@hots/workflow-policy-kit | 0.2.0 | 0.2.0 | Sama | 0 | Timeout policy only; reuse backend workflow for editorial QC. | 1.Frontend/packages/workflow-policy-kit
@hots/tenant-contracts | 0.1.0-cineva.1 | 0.1.0 | Sama | 0 | Reuse canonical scope; keep program/company semantics. | 1.Frontend/packages/tenant-contracts
@hots/tenant-client | 0.1.0-cineva.1 | Tidak ada | Satu sisi tidak tersedia | 4 | Cineva local package; not an upstream release. | 1.Frontend/packages/tenant-client
@hots/transaction-kit | 0.2.0 | 0.2.0 | Berbeda | 2 | Reuse kernel; add delayed scheduling/lease/recovery via adapter; schema gates. | 2.Backend/packages/transaction-kit
@hots/tenant-server | 0.1.0-cineva.1 | 0.1.0 | Berbeda | 8 | Review differences before adoption; real endpoint/worker scope acceptance required. | 2.Backend/packages/tenant-server
@hots/notification-kit | 0.1.0-cineva.1 | Tidak ada | Satu sisi tidak tersedia | 4 | Cineva local extraction; SSE progress, not execution scheduler. | 2.Backend/packages/notification-kit
@hots/submission-kit | Tidak ada | 0.1.0 | Satu sisi tidak tersedia | 9 | Not selected: Event public submission is not editorial review. | 2.Backend/packages/submission-kit
Verifikasi lokal | Lulus | Gagal | Batas
test:generic-packages | 44 | 0 | Synthetic package and consumer tests; package TypeScript diagnostics 0
test:packages | 17 | 0 | Existing frontend contract suite; table sources under 1000 lines
transaction-kit node --test kernel/programs/problem | 23 | 0 | Memory database and SQL-shape tests; no real MySQL
Sumber detail: knowledge architecture/content_studio_implementation_plan_2026_10_22.md dan package-evidence.json.